## Sheet1
Poornima College of Engineering(Group Number-6)
Department of Information Technology
Product Backlog (Project-II: 2018-19)
Epic | Sprint | User Story Role | User Story Name | Story Details | Tasks Items | Analyst / Prep work | Dev. Estimate | QA | Total User Story Hours
Shellinabox | 1 | All user | Create Main Page | The service provider will allow the end user to access all the services related to data analytics and cloud | 1. Define the GUI of the home page of Shellinabox. 2. Obtain the content that gives user to access the website by signing up and logining. 3.Provide several other options related to Analytics and cloud services | 2 | 5 | 3 | 10
Shellinabox | 1 | All user | Create login page for users | There are 3 ways in which a user can – face authentication, speech recognition , -password and signup if not already registered. | 1. Develop a registration form for an unsigned user which contains certain mandatory () and optional () fields. 2. Registered User is required to provide using user-id or password if sign-in option is through user id method. 3. Request each user to store his voice at the time of signup. 4. Request each user to capture his image at the time of signup using webcam. 5. Request user to sign in if they already registered | 6 | 15 | 9 | 30
Shellinabox | 2 | All user | Name of all services | User can select those services which they want to use. | 1. Upload and process the data. 2. Cloud services | 3 | 5 | 5 | 13
Shellinabox | 2 | UP.user | Registered user can upload data on cloud or process their already uploaded data. | User can select their file or folder for upload or choose the way of processing the data like in table format or graphically. | 1. Upload the data on cloud . 2. Processing on data which is already uploaded. 3. The data will be processed as per requirment | 5 | 15 | 7 | 27
Shellinabox | 3 | Cloud.users | All cloud services menu | There are different kind of cloud services,users can select any services which they want | Different options will be popped up and user can user the service which they want as per requirement:- 1. Platform as a service, 2.Container as a service 3.Software as a service , 4.Storage as a service 5.Infrastructure as a service | 3 | 5 | 2 | 10
Shellinabox | 3 | P.users | User can select their given platform. | There are different platforms given like Python,java,scala,etc | 1.DropDown list will be shown and user can select any services he wants like Python ,scala ,php,java. 2.The container will be launched for the user according to the service selected. 3. The ansible playbook will be runned in the background for the user. | 5 | 15 | 5 | 25
Shellinabox | 3 | St.User | Users can enter the size of storage they want | The user is required to tell the amount of storage they want on cloud. | 1.Enter the size of storage. 2. The storage will be provided to the user and in background the developer will provide the storage by doing partition using linux commands and runing his ansible playbooks. | 5 | 15 | 5 | 25
Shellinabox | 4 | S.User | User can select the software which they want | Here user see a software menu,in which user can select a single software or multiple software for their use. | 1. DropDown list will be shown and user can select any services he wants like Jupyter Notebook ,Firefox ,Google Chrome. 2 .The container will be launched for the user as per service asked by user. 3. The ansible playbook will be runned in the background for the user. | 5 | 15 | 5 | 25
Shellinabox | 4 | C.user | User can select the image of their container | The user will tell which image they want of the container they want like ubuntu,centos. | 1. DropDown list will be shown and user can select any services he wants like Centos ,Ubuntu. 2 .The container will be launched for the user as per service asked by user. 3. The ansible playbook will be runned in the background for the user. | 5 | 15 | 5 | 25
Shellinabox | 5 | Developer | Link All the web Pages with the Main Servcie Page | All the separate Pages are connected to main page | 1. Connect All web Pages 2. Testing | 4 | 5 | 5 | 14
Shellinabox | 5 | Admin | Documentation | All the Documentation of Shellinabox will be done | 1. All the Documentation 2. Testing | 5 | 10 | 5 | 20
Shellinabox | 6 | Admin | Feedback | All user will give Feedback according to their use | 1. Create a feedback window for users 2. Testing | 5 | 6 | 5 | 16
Total | [5 empty] | 53 | 126 | 61 | 240
* Remark: Following abbreviations have been used in Product Backlog 1. P.User - Platform User 2. S. User - Software User 3. C. User - Container User 4. St. User - Storage (Database) User 5. UP User - Upload & Process User
Mr. Amol Saxena Vijaya Nandwana (Project Guide) (Scrum Master) Mr. Shirish Nagar (Project Coordinator)